***Sprint backlogs***

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint backlog 1 | | | | | | | | | | | | |
| User Story | Task | Member | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 |
| **Creating an account** | Making a registration page | Jan, Denis | 10 | 8 | 7 | 5 | 4 | 2 | 0 | 0 | 0 | 0 |
| Coding to add new account into database | Valentin | 12 | 12 | 11 | 10 | 8 | 6 | 4 | 2 | 0 | 0 |
| Coding to add bank account to the account | Valentin | 12 | 11 | 10 | 9 | 7 | 6 | 3 | 2 | 0 | 0 |
| **Logging in to the account** | Making a login page | Denis, Valentin | 10 | 8 | 7 | 5 | 4 | 4 | 3 | 1 | 0 | 0 |
| Checking if the email and password matches | Denis | 12 | 13 | 12 | 10 | 10 | 9 | 7 | 5 | 3 | 0 |
| Making log in button working | Jan | 10 | 11 | 10 | 9 | 7 | 6 | 4 | 3 | 1 | 0 |
| **Logging off** | Making Log out button working | Jan | 10 | 10 | 9 | 8 | 7 | 7 | 5 | 4 | 3 | 0 |
| **Total hours:** | | | **80** | **73** | **66** | **56** | **47** | **40** | **26** | **17** | **7** | **0** |

|  |  |
| --- | --- |
| **Sprint Length** | 2 weeks |
| **Workdays During Sprint** | 9 days |

|  |  |  |  |
| --- | --- | --- | --- |
| **Team Member** | **Available days during Sprint** | **Available hours per day** | **Total available hours during Sprint** |
| Jan | 4 days | 5 hours | 20 hours |
| Denis | 6 days | 6 hours | 36 hours |
| Valentin | 6 days | 4 hours | 24 hours |
| Effective/Ideal hours: | | | 80 hours |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint backlog 2 | | | | | | | |
| User Story | Task | Member | Estimate | Day 1 | Day 2 | Day 3 | Day 4 |
| **User choosing to donate to a disaster** | Making a disaster page | Valentin, Jan | 8 | 5 | 2 | 1 | 0 |
| Code to donate to a single disaster | Valentin | 14 | 10 | 7 | 3 | 0 |
| Check if user is log in already | Valentin | 8 | 5 | 3 | 1 | 0 |
| Check if the amount is less than the balance | Jan | 10 | 7 | 4 | 2 | 0 |
| **Shopping basket - put** | Making a shop page | Jan | 5 | 4 | 3 | 1 | 0 |
| Code for adding item in order line | Denis | 7 | 4 | 3 | 1 | 0 |
| Code for creating an order line | Denis | 6 | 5 | 4 | 1 | 0 |
| Code for creating an order | Denis | 7 | 7 | 9 | 10 | 10 |
| **Total hours:** | | | **67** | **47** | **35** | **20** | **10** |

|  |  |
| --- | --- |
| **Sprint Length** | 1 weeks |
| **Workdays During Sprint** | 4 days |

|  |  |  |  |
| --- | --- | --- | --- |
| **Team Member** | **Available days during Sprint** | **Available hours per day** | **Total available hours during Sprint** |
| Jan | 3 days | 5 hours | 15 hours |
| Denis | 4 days | 6 hours | 24 hours |
| Valentin | 4 days | 7 hours | 28 hours |
| Effective/Ideal hours: | | | 67 hours |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint backlog 3 | | | | | | | |
| User Story | Task | Member | Estimate | Day 1 | Day 2 | Day 3 | Day 4 |
| **Shopping basket - put** | Code for creating an order | Denis | 10 | 9 | 6 | 6 | 0 |
| **Remove items from basket** | Implement the deleting order line | Denis | 2 | 2 | 0 | 0 | 0 |
| Code to return the stock to the product | Denis | 2 | 2 | 2 | 2 | 3 |
| **Pay for the items** | Assign the order id to each order line | Valentin | 3 | 3 | 2 | 0 | 0 |
| Implement the transfer of the money | Valentin | 7 | 7 | 7 | 7 | 8 |
| **Inserting new item(s)** | Making a manage page design | Valentin | 2 | 0 | 0 | 0 | 0 |
| Making the product manage page design | Jan | 2 | 0 | 0 | 0 | 0 |
| Code to add new item in the database | Jan | 3 | 3 | 4 | 3 | 3 |
| **Removing existing item(s)** | Implement to delete item from database | Denis | 5 | 5 | 3 | 0 | 0 |
| **Updating existing item(s)** | Code to update the desired item in database | Jan | 7 | 8 | 7 | 5 | 5 |
| **Adding new disaster** | Making the disaster manage page design | Jan | 2 | 0 | 0 | 0 | 0 |
| Code to add new disaster in the database | Jan | 6 | 5 | 4 | 2 | 2 |
| **Updating existing disaster** | Code to update the desired item in database | Valentin | 7 | 6 | 5 | 2 | 0 |
| **Updating account** | Making profile page design | Jan, Valentin | 2 | 1 | 0 | 0 | 0 |
| Code to update the desired fields in the user profile in database | Valentin | 5 | 5 | 3 | 3 | 4 |
| **Check the disasters** | Implement the permission access | Denis | 1 | 1 | 0 | 0 | 0 |
| **Viewing a list of the user’s accounts** | Code to show all the available users in the system | Jan | 2 | 2 | 0 | 0 | 0 |
| **Deleting user’s account** | Implement to delete user from database | Valentin | 5 | 5 | 6 | 6 | 5 |
| **Editing a user’s profile** | Code to update the desired user in database | Jan | 7 | 7 | 5 | 3 | 0 |
| **User viewing the list of disaster** | Code to show all the available disasters in the system | Denis | 5 | 5 | 4 | 1 | 0 |
| **Checking information about chosen disaster** | Implement the permission access | Valentin | 2 | 2 | 0 | 0 | 0 |
| **Viewing account** | Implement the permission access | Denis | 2 | 2 | 0 | 0 | 0 |
| **View my basket** | Code to show all the available order lines in the current order to the user | Valentin | 1 | 0 | 0 | 0 | 0 |
| **Total hours:** | | | **96** | **80** | **58** | **40** | **30** |

|  |  |
| --- | --- |
| **Sprint Length** | 1 weeks |
| **Workdays During Sprint** | 4 days |

|  |  |  |  |
| --- | --- | --- | --- |
| **Team Member** | **Available days during Sprint** | **Available hours per day** | **Total available hours during Sprint** |
| Jan | 4 days | 8 hours | 32 hours |
| Denis | 4 days | 8 hours | 32 hours |
| Valentin | 4 days | 8 hours | 32 hours |
| Effective/Ideal hours: | | | 96 hours |