***Sprint backlogs***

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint backlog 1 | | | | | | | | | | | | |
| User Story | Task | Member | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 |
| **Creating an account** | Making a registration page | Jan, Denis | 10 | 8 | 7 | 5 | 4 | 2 | 0 | 0 | 0 | 0 |
| Coding to add new account into database | Valentin | 12 | 12 | 11 | 10 | 8 | 6 | 4 | 2 | 0 | 0 |
| Coding to add bank account to the account | Valentin | 12 | 11 | 10 | 9 | 7 | 6 | 3 | 2 | 0 | 0 |
| **Logging in to the account** | Making a login page | Denis, Valentin | 10 | 8 | 7 | 5 | 4 | 4 | 3 | 1 | 0 | 0 |
| Checking if the email and password matches | Denis | 12 | 13 | 12 | 10 | 10 | 9 | 7 | 5 | 3 | 0 |
| Making log in button working | Jan | 10 | 11 | 10 | 9 | 7 | 6 | 4 | 3 | 1 | 0 |
| **Logging off** | Making Log out button working | Jan | 10 | 10 | 9 | 8 | 7 | 7 | 5 | 4 | 3 | 0 |
| **Total hours:** | | | **80** | **73** | **66** | **56** | **47** | **40** | **26** | **17** | **7** | **0** |

|  |  |
| --- | --- |
| **Sprint Length** | 2 weeks |
| **Workdays During Sprint** | 9 days |

|  |  |  |  |
| --- | --- | --- | --- |
| **Team Member** | **Available days during Sprint** | **Available hours per day** | **Total available hours during Sprint** |
| Jan | 4 days | 5 hours | 20 hours |
| Denis | 6 days | 6 hours | 36 hours |
| Valentin | 6 days | 4 hours | 24 hours |
| Effective/Ideal hours: | | | 80 hours |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint backlog 2 | | | | | | | |
| User Story | Task | Member | Estimate | Day 1 | Day 2 | Day 3 | Day 4 |
| **User choosing to donate to a disaster** | Making a disaster page | Valentin, Jan | 8 | 5 | 2 | 1 | 0 |
| Code to donate to a single disaster | Valentin | 14 | 10 | 7 | 3 | 0 |
| Check if user is log in already | Valentin | 8 | 5 | 3 | 1 | 0 |
| Check if the amount is less than the balance | Jan | 10 | 7 | 4 | 2 | 0 |
| **Shopping basket - put** | Making a shop page | Jan | 5 | 4 | 3 | 1 | 0 |
| Code for adding item in order line | Denis | 7 | 4 | 3 | 1 | 0 |
| Code for creating an order line | Denis | 6 | 5 | 4 | 1 | 0 |
| Code for creating an order | Denis | 7 | 7 | 9 | 10 | 10 |
| **Total hours:** | | | 60 | 47 | 35 | 20 | 10 |

|  |  |
| --- | --- |
| **Sprint Length** | 1 weeks |
| **Workdays During Sprint** | 4 days |

|  |  |  |  |
| --- | --- | --- | --- |
| **Team Member** | **Available days during Sprint** | **Available hours per day** | **Total available hours during Sprint** |
| Jan | 3 days | 4 hours | 12 hours |
| Denis | 4 days | 6 hours | 24 hours |
| Valentin | 4 days | 6 hours | 24 hours |
| Effective/Ideal hours: | | | 60 hours |