## Sheet1
Sprint 1
User Story | Tasks | Member | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
User choosing to donate to a disaster | Making the disaster page | Valentin | bar: Day 8
| Coding to get list of disasters | Valentin | Day 7: 3; Day 8: 2
Shopping basket put | Making the shop page | Jan, Denis | bar: Day 8
| Coding to get list of products | Valentin, Denis | Day 7: 3; Day 8: 1
Creating an account | Making a registration page | Valentin
| Coding to confirm the password | Valentin
| Coding to check cvc is a number | Valentin
| Coding to check account is a number | Valentin
Logging in to the account | Making a login page | Valentin
| Checking if the uname matches password | Valentin
Sprint 2
User Story | Tasks | Member | Day 1: Day 1; Day 2: Day 2; Day 3: Day 3; Day 4: Day 4
Logging off | Coding to get the log off function | Valentin
User choosing to donate to a disaster